## Task Management Tabular Data
SUMMARY
Completed Tasks Count |  |  | 3 | 3
Average Completion |  |  | 59.38% | 59.38%
Department | Task | Assigned To | Year | Start Date | Year Due | Due Date | Status | Priority | Hours Spent | Budget ($) | Completion % | Days Remaining | Over-Budget Flag | Task Duration
Finance | Prepare Q2 Report | Ahmed | 2026‑06‑01 | 2026-06-01 | 2026‑06‑14 | 2026-06-14 | In Progress | High | 12 | 4500 | 65% | -1 | OK | 13
HR | Update Employee Records | Sarah | 2026‑06‑03 | 2026-06-03 | 2026‑06‑10 | 2026-06-10 | Completed | Medium | 6 | 1200 | 100% | 0 | OK | 7
IT | System Maintenance | John | 2026‑06‑05 | 2026-06-05 | 2026‑06‑20 | 2026-06-20 | Delayed | High | 15 | 7800 | 40% | 5 | OK | 15
Admin | Office Supply Audit | Fatima | 2026‑06‑02 | 2026-06-02 | 2026‑06‑07 | 2026-06-07 | Completed | Low | 3 | 350 | 100% | 0 | OK | 5
Finance | Budget Forecasting | Ahmed | 2026‑06‑10 | 2026-06-10 | 2026‑06‑25 | 2026-06-25 | In Progress | High | 8 | 5200 | 50% | 10 | OK | 15
HR | Training Session Prep | Sarah | 2026‑06‑12 | 2026-06-12 | 2026‑06‑18 | 2026-06-18 | Not Started | Medium | 0 | 900 | 0% | 3 | OK | 6
IT | Software Updates | John | 2026‑06‑15 | 2026-06-15 | 2026‑06‑30 | 2026-06-30 | In Progress | High | 5 | 3600 | 20% | 15 | OK | 15
Admin | Meeting Coordination | Fatima | 2026‑06‑01 | 2026-06-01 | 2026‑06‑03 | 2026-06-03 | Completed | Low | 2 | 150 | 100% | 0 | OK | 2
SUMMARY
Status | Count of Status | [5 empty] | Department | Sum of Hours Spent |  |  |  | Assigned To | Sum of Budget ($) | Sum of Hours Spent
Completed | 3 | [5 empty] | Admin | 5 |  |  |  | Ahmed | 9700 | 20
Delayed | 1 | [5 empty] | Finance | 20 |  |  |  | Fatima | 500 | 5
In Progress | 3 | [5 empty] | HR | 6 |  |  |  | John | 11400 | 20
Not Started | 1 | [5 empty] | IT | 20 |  |  |  | Sarah | 2100 | 6
Grand Total | 8 | [5 empty] | Grand Total | 51 |  |  |  | Grand Total | 23700 | 51
Across the Finance, HR, IT, and Administrative departments, a total of eight operational tasks were monitored to assess progress, workload distribution, and overall performance. The data shows a balanced mix of completed work, ongoing initiatives, and areas requiring attention. Four tasks were fully completed, demonstrating strong execution within the HR and Administrative units. These completed tasks include employee record updates, office supply auditing, and meeting coordination, all of which reached 100% completion with efficient use of time and budget. Three tasks are currently in progress, primarily within the Finance and IT departments. These include the preparation of the Q2 financial report, budget forecasting, and software updates. Progress levels range from 20% to 65%, indicating steady advancement but also highlighting the need for continued focus to meet upcoming deadlines. One task: system maintenance within IT, is marked as delayed, with only 40% completion. This delay suggests potential resource constraints or technical challenges that may require managerial intervention. The HR department has one task that has not yet started: preparation for an upcoming training session. This item represents an opportunity for early action to avoid future bottlenecks. In total, 51 hours of work have been logged across all departments, with a combined budget allocation of $23,700. The overall completion rate across all tasks stands at approximately 59%, reflecting moderate progress toward departmental goals. Finance remains heavily engaged with two major ongoing tasks, while HR shows mixed progress with one completed and one pending. IT displays the most variability, with one delayed task and one in progress. The Administrative department demonstrates strong performance, having completed all assigned tasks. Overall, the dataset reflects a productive workflow with clear indicators of where attention and resources should be directed next.
Formulas:
Start Date = DATE(LEFT([Year],4),MID([Year],6,2),RIGHT([Year],2))
Due Date = DATE(LEFT([Year Due],4),MID([Year Due],6,2),RIGHT([Year Due],2))

## Task Management Dashboard
This shape represents a slicer. Slicers are not supported in this version. Please update to the latest version of WPS Office.
This shape represents a slicer. Slicers are not supported in this version. Please update to the latest version of WPS Office.
This shape represents a slicer. Slicers are not supported in this version. Please update to the latest version of WPS Office.